## Summary
Assignment coverage summary
| Met | Partial | Not met | Total
Brief lines (Requirements tab) | 25 | 4 | 0 | 29
Success criteria | 4 | 0 | 1 | 5
Open items to close
Boundary paragraph in write-up failure cases (~30 min)
One ~2M-face run to cover the full input range (~15 min)
CUDA timing on the GTX 1650 (optional)
Feature coverage 73.1% vs 90%: documented with measured limits (docs/crease_bounds.md)

## Requirements
Quad remeshing assignment: line-by-line coverage
Checked against the repo (main) and benchmark/results/summary.json on 16 Oct 2026. Status: Met / Partial / Not met.
# | Section | Requirement (from the brief) | Status | Evidence | Where in the repo | Gap / next step
1 | Objective | Preserve geometry: faithful to the input surface | Met | Mean distance 0.086% of bbox diagonal (Instant Meshes 0.316%) | src/postprocess.cpp relax_and_project
2 | Objective | Preserve sharp features | Partial | Feature coverage 73.1% mean; >= 90% on 5 models (fandisk, spot, sheen chair, velvet sofa, leather sofa) | src/features.cpp, src/crease_cut.cpp | See Success criteria: coverage below 90%
3 | Objective | Edge flow follows principal curvature and feature lines | Met | Cross field locked to creases; principal-curvature alignment | src/field.cpp principal_directions, --curvature-weight
4 | Objective | Minimal, well-placed irregular vertices (valence != 4) | Met | Fewer singularities than Instant Meshes on 14/15 models (count and per 1k faces) | QuadriFlow min-cost flow (src/qflow_driver.cpp) | Lounge room loses (968 vs 867)
5 | Objective | Near-square, planar quads | Met | Mean scaled Jacobian 0.903 (lowest model 0.82); planarity 0.002-0.032 | src/metrics.cpp
6 | Objective | Controllable size and density | Met | -f / -e for size; --density, --density-region, --curvature-density | apps/quadremesh_cli.cpp
7 | Input | .obj / .ply / .glb | Met | Also .gltf and .off | src/io.cpp load_mesh
8 | Input | 10K-2M faces | Partial | Tested 12.9K to 1.03M faces (fountain scan) | benchmark/results/summary.json | Run one ~2M-face input and record runtime
9 | Input | Noise, small holes, non-manifold edges, multiple components | Met | Preprocess repairs all of these; noisy/non-manifold test passes; fandisk_noisy and scans in benchmark | src/preprocess.cpp, tests
10 | Input | Control: target quad count or edge length | Met | -f N / -e X | apps/quadremesh_cli.cpp
11 | Input | Control: sharp-feature angle threshold | Met | -a DEG (default 35) | apps/quadremesh_cli.cpp
12 | Input | Control: guidance strokes or curves | Met | --strokes FILE, --strokes-as-edges; demo image | docs/report/demo_strokes.png
13 | Input | Control: adaptive density map | Met | --density FILE, --density-region; demo image | docs/report/demo_density.png
14 | Input | Control: symmetry hint | Met | --symmetry x¦y¦z, exactly mirrored output; demo image | docs/report/demo_symmetry.png
15 | Output | Quad mesh (.obj) | Met | 100% quads by default; --pure-quad guarantees it | src/io.cpp save_quad_obj
16 | Output | Optional UVs / attributes transferred from source | Met | UV transfer respecting chart seams; generic per-vertex attributes | src/transfer.cpp
17 | Output | Quality report (JSON) with the metrics | Met | --report FILE.json | src/metrics.cpp evaluate
18 | Constraints | Open boundaries kept as quad edges | Partial | Boundaries constrained in the field, but measured boundary coverage is low on some models: velvet sofa 1.6%, scans ~9%, bunny 49% (IM 0-16%) | src/field.cpp, src/postprocess.cpp | Add a boundary paragraph to write-up failure cases
19 | Constraints | Deterministic for same input and parameters | Met | test_deterministic; Instant Meshes fallback single-threaded deterministic | tests/test_python.py, src/im_driver.cpp
20 | Constraints | Core in C++ (libigl / Eigen) | Met | C++17 core on Eigen + libigl | src/
21 | Constraints | Python bindings (pybind11) | Met | 6 Python tests pass | python/bindings.cpp, python/quadremesh/api.py
22 | Constraints | Optional PyTorch learned field prediction | Met | Learned guide field, opt-in | python/quadremesh/learned.py
23 | Constraints | Runs headless on Linux | Met | All builds, tests and benchmarks run headless | CMakeLists.txt
24 | Constraints | Optional CUDA path for field optimization | Partial | Code supports CUDA via PyTorch; only run on CPU | python/quadremesh/torch_field.py | Time GPU vs CPU on the GTX 1650 (CHECKPOINT open item 2)
25 | Deliverables | 1. CLI tool and Python API quadremesh(input, target_faces, feature_angle, ...) | Met | quadremesh CLI and Python quadremesh() | apps/quadremesh_cli.cpp, python/quadremesh/api.py
26 | Deliverables | 2. Evaluation script outputting all metrics | Met | quadeval / evaluate() | apps/quadeval_cli.cpp, src/metrics.cpp
27 | Deliverables | 3. Benchmark vs Instant Meshes, QuadriFlow, Blender on >= 10 models incl. furniture or room scans | Met | 15 models incl. 4 furniture and 2 room-scale scans; QuadriFlow 12/15 ok, Blender 8/15, ours 15/15 | benchmark/run_benchmark.py, benchmark/results/
28 | Deliverables | 4. Visual report: field, singularity overlay, scaled-Jacobian heatmap | Met | All three panels per model, re-rendered 16 Oct; plus web walkthrough | docs/report/, web/
29 | Deliverables | 5. Write-up: design choices, failure cases, future work | Met | Sections 2, 6 and 7 | docs/technical_writeup.pdf

## Success criteria
Success criteria (benchmark mean, 15 models)
Criterion | Target | Direction | Result | Pass? | Instant Meshes | Note
Quads | 98% | >= | 100% | Met | 100% | Default setting; max coverage 99.4%
Mean scaled Jacobian | 0.8 | >= | 0.903 | Met | 0.935 | Lowest model 0.82
Mean distance error (% of bbox diagonal) | 0.5 | < | 0.086 | Met | 0.316 | Values are percentages
Feature coverage | 90% | >= | 73.1% | Not met | 22.1% | Max-coverage setting; 82.8% without the 2 room scans; >= 90% on 5 models
Models with fewer singularities than Instant Meshes | 8 | >= | 14 | Met | - | Out of 15 (majority = 8). Totals 3,276 vs 4,782; leather sofa IM made only 844 faces
Blue = values from benchmark/results/summary.json (generated tables in README.md). Pass? is a formula.